## Slide 1: AI Governance Readiness Review
Executive operating model for enterprise adoption
May 2026
Enterprise AI Office
Strategy and Risk Enablement

## Slide 2: Current State
Where the operating model needs executive attention
01

## Slide 3: Discussion Flow
Adoption signals and risk exposure
Governance model and decision rights
Control maturity and implementation roadmap
Executive decisions requested
From current-state risk to the next operating cadence

## Slide 4: Governance Model Shift
Current pattern
Target pattern
Teams run isolated pilots with uneven review depth and limited reuse of controls.
A repeatable intake, review, and evidence model supports faster scaled deployment.
Moving from local experimentation to enterprise-grade control
Policy interpretation varies by business unit
Model and data reviews are often manual
Evidence collection happens late in the delivery cycle
One intake standard for risk classification
Control templates embedded in product delivery
Continuous evidence capture for audit readiness

## Slide 5: Priority Workstreams
Translate AI policy into intake questions, review checkpoints, and evidence artifacts.
Standardize logging, prompt review, data boundary controls, and model access approvals.
Establish weekly triage, monthly risk review, and quarterly executive steering.
Three workstreams should be managed as one program
Policy to workflow
Platform controls
Operating cadence

## Slide 6: Control Maturity by Quarter
Chart: 
| Q1 | Q2 | Q3 | Q4
Intake coverage | 35 | 58 | 76 | 90
Evidence automation | 18 | 36 | 61 | 82
Target state assumes controls become reusable assets by Q4
Scores represent estimated percentage coverage across prioritized AI use cases.

## Slide 7: Decision Register
Decision | Owner | Timing | Impact
Approve common intake taxonomy | AI Steering Committee | May | Enables portfolio reporting
Mandate evidence template | Risk and Compliance | June | Reduces audit preparation time
Fund control automation | Technology | July | Improves release throughput
Launch monthly control review | Business Operations | July | Creates sustained accountability
Decisions required to move from pilots to repeatable production governance
Each decision is scoped to reduce delivery friction while increasing control consistency.

## Slide 8: Implementation Roadmap
Weeks 1-2: confirm policy taxonomy and business-unit intake owners
Weeks 3-6: publish control templates and evidence examples
Weeks 7-10: automate logging and approval-state capture in delivery tooling
Weeks 11-12: run first executive readiness review with exception tracking
Build the governance muscle without slowing approved delivery

## Slide 9: Operating Model Signal
A single operating dashboard should show use-case stage, risk class, control evidence, and release decision.
One visible system of accountability should replace fragmented local trackers
Internal operating model concept for executive review.

## Slide 10: Appendix: Readiness Criteria
These criteria define whether an AI use case can move from pilot to controlled production use.
Enterprise AI Policy v2.1
Model Risk Review Checklist
Security Logging Standard
Minimum conditions for production approval
Intake classification completed
Data boundary reviewed
Human oversight documented
Prompt and model evaluation evidence attached
Incident owner and rollback path assigned

## Slide 11: Executive Decisions Requested
Approve the next operating-model phase
Confirm governance scope, control automation funding, and review cadence.
Enterprise AI Office
Approve phase 2 mobilization by June 7